## Read and Understand the Rule
Instructions:
- Review each resource
- Initial and date. Add follow up notes if appropriate.
Resource | Date | Initials | Notes
FSMA 204: Beginning January 20, 2026, the Food Traceability Rule requires covered entities (§ 1.1300) who manufacture, process, pack, or hold foods on the Food Traceability List (FTL), to:
Develop a Traceability Plan (§ 1.1315)
Assign Traceability Lot Codes (§1.1320)
Maintain Records of Critical Tracking Events
Harvesting & Cooling (§1.1325)
Initial Packing of Raw Agricultural Commodities (§1.1330)
First Land-Based Receiver of an FTL Food from a Fishing Vessel (§1.1335)
Shipping (§1.1340)
Receiving (§1.1345)
Transformation (§1.1350)
Maintain and make available traceability records according to the following requirements (§1.1455)
Understand the consequences for a covered entity failing to comply, as outlined in §1.1460
Understand procedures for Modified Requirements and Exemptions, and Waivers.
Existing exemptions are listed in (§ 1.1305).
Foods not covered by this rule are covered by the Bioterrorism Act of 2002 (Subpart J).
FDA Resources
FSMA Final Rule on Requirements for Additional Traceability Records for Certain Foods ¦ FDA
Industry Best Practices:
GS1 US Guideline with EDI and EPCIS Templates
FMI Guidance
Produce Industry Guidance
Seafood Guide to FDA FSMA 204 Traceability Rule
FDA’s Food Traceability Rule ¦ National Restaurant Association

## Review the FTL
Instructions:
- Review each food you manufacture, process, pack, or hold, including ingredients that make up finished product
- Indicate whether foods and/or ingredients are covered by the rule
- Indicate whether the finished product is covered by the rule
- Note customers and suppliers
- See example below
Foods
SKU | Description | FTL | FTL Food Category | Customer(s)
1111 | Roma Tomatoes | Y | Toamtoes (fresh) | Friendly Grocery
2222 | Grape Tomatoes | Y | Tomatoes (fresh) | Friendly Grocery
3333 | Cucumbers | Y | Cucumbers | Quick Shop
4444 | Green Bell Peppers | Y | Peppers | Friendly Grocery
5555 | White Onions (fresh cut) | Y | Vegetables (fresh-cut) | Friendly Grocery
6666 | Jalepeños | Y | Vegetables (fresh-cut) | Friendly Grocery
7777 | Potatoes | N | Exempt | Quick Shop
8888 | Basil | Y | Herbs (fresh) | Quick Shop
9999 | Cilantro | Y | Herbs (fresh) | Friendly Grocery
1011 | Limes | N | Exempt | Friendly Grocery
Ingredients in Fresh Pico de Gallo
SKU | Description | FTL | FTL Food Category | Supplier(s)
1111 | Roma Tomatoes | Y | Toamtoes (fresh) | Red Produce
5555 | Onions (fresh cut) | Y | Vegetables (fresh-cut) | Aromatic Onions
9999 | Cilantro | Y | Herbs (fresh) | Herbs-R-Us
6666 | Jalepeños | Y | Vegetables (fresh-cut) | Hot Pepper Produce
1011 | Lime (juice) | N | Exempt | Green Lime Farm
Final Product (Fresh Pico de Gallo)
SKU | Description | FTL | FTL Food Category | Customer(s)
9876 | Fresh Pico de Gallo | Y | Multi-ingredient (fresh) | Friendly Grocery

## Determine Customer Requirements
Instructions:
- Receive and review customer requirements for sending Shipping KDEs
- Capture those requirements in the spreadsheet below
Customer Requirements
Category | Name | Link to Document | Date Reviewed | Product Master Data Sharing | Location Master Data Sharing | Shipping KDE Data Sharing
Grocery | ABC | {link} | 2024-03-18 | Share with Shipping KDEs | Share with Shipping KDEs | EDI 856 only
Grocery | DEF | {link} | 2024-03-18 | Share via GDSN | Share through GS1 Data Hub | EDI or EPCIS (no paper)
Grocery | GHI | {link} | 2024-03-18 | Share via Portal | Share via Portal | Paper or EDI
Grocery | JKL | {link} | 2024-03-18 | Share via Traceability Network | Share via Traceability Network | Trace Network only

## Evaluate Current Systems
Instructions:
- Check each internal system related to food traceability
- Indicate conformant (Green), partially conformant (Yellow), non-conformant (Red)
Receiving
KDEs
Systems | Rec Dt | Ref Doc | From | To | Prod Desc | TLC | Source | Qty | UOM
Purchasing |  |  | N/A |  |  | N/A | N/A
Receiving
WMS
Processing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Sales | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Order Processing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Logistics | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Accounting | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Shipping
KDEs
Systems | Ship Dt | Ref Doc | From | To | Prod Desc | TLC | Source | Qty | UOM
Purchasing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Receiving | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WMS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Processing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Sales
Order Processing
Logistics
Accounting | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Transformation
Input KDEs
Systems |  |  |  | Input SKU | Input Desc | TLC | Qty | UOM
Purchasing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Receiving | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WMS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Processing | N/A | N/A | N/A
Sales | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Order Processing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Logistics | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Accounting | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Output KDEs
Systems | Proc Dt | Ref Doc | Location | Output SKU | Output Desc | TLC | Qty | UOM
Purchasing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Receiving | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WMS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Processing
Sales | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Order Processing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Logistics | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Accounting | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KDE | Shipping | Receiving | Transformation
|  |  | Food Used | Food Produced
Traceability Lot Code | X | X | X | X
GS1-128 Barcode, RFID, or IoT Device: AI(01) GTIN + AI(10) Lot
Traceability Lot Code Source or Source Reference | X | X | - | X
Packing or Processing Location Description or reference (e.g., GLN or URL)
Product Description | X | X | X | X
Brand name, Commodity, Variety, Pack Size/Style
For seafood, species and/or acceptable market name.
Quantity and Unit of Measure | X | X | X | X
(e.g.,6 cases, 25 reusable plastic containers, 200 pounds)
Physical Location(s) Description | Ship-To | Ship-To | Transformation Location
Key contact information - the business name, phone number, physical location address (or geographic coordinates), and city, State, and zip code, country or comparable information for foreign locations. | Ship-From | Ship-From
Reference Document Type and Number | X | X | X
(e.g., Purchase Orders, Bills of Lading, ASNs, Work Orders)
Date | Ship Date | Rec Date | Transform Date

## Determine Supplier Sharing Cap
Instructions:
- Determine each supplier's capability for sending Shipping KDEs
- Indicate digitally (Green), paper (Yellow), non-conformant (Red)
Supplier Shipping KDE Data Sharing Capability
KDEs
Suppliers | Ship Dt | Ref Doc | From | To | Prod Desc | TLC | Source | Qty | UOM
Supplier 1
Supplier 2
Supplier 3
Supplier 4
Supplier 5
Supplier 6
Supplier 7
Supplier 8

## GAP Analysis
Instructions:
- Complete analysis
- Indicate % conformant based on your evaluation criteria
- Update Monthly or Quarterly
Data Collection and Sharing
| 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01
Product Master Data System | 15 | 25 | 35 | 40 | 80 | 85
Location Master Data System | 25 | 30 | 35 | 40 | 45 | 50
KDE Collection Systems | 50 | 55 | 60 | 65 | 70 | 75
KDE Sharing Systems | 10 | 15 | 20 | 25 | 30 | 35
Suppliers | 30 | 35 | 40 | 45 | 50 | 55
Customers | 0 | 5 | 10 | 15 | 20 | 25
Procedures and Training
| 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01
Leadership | 20 | 25 | 30 | 35 | 40 | 45
Purchasing | 35 | 40 | 45 | 50 | 55 | 60
Receiving | 50 | 55 | 60 | 65 | 70 | 75
Inventory | 35 | 40 | 45 | 50 | 55 | 60
Picking | 55 | 60 | 65 | 70 | 75 | 80
Shipping | 50 | 55 | 60 | 65 | 70 | 75
Order Processing | 15 | 20 | 25 | 30 | 35 | 40

## Traceability Plan
Traceability Plan (§ 1.1315)
If you are subject to the requirements of the final rule, you must establish and maintain a traceability plan containing the following information:
1. A description of the procedures you use to maintain the records you are required to keep under this rule, including the format and location of these records.
2. A description of the procedures you use to identify foods on the Food Traceability List that you manufacture, process, pack, or hold;
3. A description of how you assign traceability lot codes to foods on the Food Traceability List, if applicable;
4. A statement identifying a point of contact for questions regarding your traceability plan and records; and
5. If you grow or raise a food on the Food Traceability List (other than eggs), a farm map showing the areas in which you grow or raise such foods.
* The farm map must show the location and name of each field (or other growing area) in which you grow a food on the Food Traceability List, including geographic coordinates and any other information needed to identify the location of each field or growing area.
* For aquaculture farms, the farm map instead must show the location and name of each container (e.g., pond, pool, tank, cage) in which you raise seafood on the Food Traceability List, including geographic coordinates and any other information needed to identify the location of each container.
6. You must update your traceability plan as needed to ensure that the information reflects your current practices and to ensure you are in compliance with the rule
7. You must retain your previous traceability plan for 2 years after you update the plan
1. Records Maintenance & Storage
| Procedure | Format | Location
Product Master Data System | When a new product is established, we assign product id's and descriptions for finished products (meals), purchased ingredients, and intermediate products (WIP). | Internal product identifiers are 10-digit, numeric. Product description is stored in a short description field, plus commodity, variety, pack size, pack style, brand. We also assign a 14 digit GS1 GTIN to identify it uniquely in global commerce. | Our Enterprise Resource Planning System contains product master and bills of material. We also share this product master to an external traceability network (link to network).
Location Master Data System | For each location managed by our organization we establish a location identifier (plant number) and location description. We can also link it to globally unique identiification numbers. We use GS1 GLNs to identify supplier managed ship-from physical locations and customer managed ship-to locations. | Location identifiers (plant numbers) are assigned in our ERP system. We can associate other identifiers to this master data record, including DUNS numbers, GS1 GLNs, and FDA Food Facility Registration Number. Supplier and Customer locations are identified with 13 digit GS1 GLNs. | Our Enterprise Resource Planning System (name of system) contains location master records for supplier locations, customer locations, and internal locations. We integrate an external traceability network that provides location GLNs and descriptions for customer and supplier locations (link to network).
Supplier Shipping KDE Sharing Systems | Suppliers may share Shipping KDEs using one of three methods: (1) Bill of lading plus case or pallet labeling (2) EDI 856 Advanced Ship Notice and pallet SSCC (3) EPCIS Shipping event with pallet SSCC. See GS1 US Best Practices. https://www.gs1us.org/industries-and-insights/by-industry/foodservice/standards-in-use/food-safety | Suppliers provide all shipping KDEs electronically, in machine readable format affixed to a case or pallet, or in human readable text on a document provided with the delivery of the food. | Digital Shipping KDEs are aggregated to an external traceability network (link to network). Machine readable KDEs affixed to cases or pallets are captured electronically during receiving and store as a receiving record (see receiving). Human readable KDEs on shipping documents are either captured manually into our receiving record (see receiving) or scanned into our document storage system (link or name of system).
Receiving KDE Collection Systems | Primary workflow: receiving clerk scans a delivered pallet's SSCC. This provides receiver with the associated Purchase Order and PO Line Number, Product Description, Traceability Lot Code and Quantity of cases on pallet. (suppliers are requested to provide one TLC per pallet or label pallets as mixed-lot for further handling). The receiver confirms that the information matches the physical product received and then prints and applies either case labels or a pallet labels with an internally assigned ID and barcode that is meaningful to our warehouse/inventory system. See (link) to full procedure with alternate receiving methods and mixed pallet receiving protocol. | Receiving KDEs are stored in both the external traceability network (link to network) as EPCIS Receiving events, and internally in our warehouse/inventory system using our internally assigned material number and plant number. Printed documents such as BOLs are captured using our document management system and linked to the order using PO/PO Line Number. | Digital Receiving Records are stored internally in our warehouse/inventory system (link or name of system), and in an external traceability network (link to network)
Transform KDE Collection Systems | Primary workflow: for each finished product to be produced a work order is generated including a list of all ingredients and quantities to be produced per bill of material. Work orders are aggregated into a raw material selection instruction with total quantity to be selected and prepared for production. As products are selected, the case barcode (assigned in prior step) is scanned and quantity confirmed via entry on mobile device. This generates "foods used in transformation" records. Finished goods quantities and new Traceability Lot Codes are generated from the Work Order when production for the day is entered by the production supervisor. This creates the "foods produced through transformation". Each new food produced is assigned a unique identifier and barcode which is captured during transformation. | Records are stored as EPCIS Transformation Events. | Transformation records are stored in the external traceability network (link to network) as a digital record containing globally unique identifiers for ingredients and finished products (GTIN-14s). The transformation location is also identiifed using a globally unique identifier (GLN).
Shipping KDE Collection and Sharing Systems | Primary workflow: for each customer order, a shipping document is produced. This shipping document indicates DC location, date, food types, and quantity of packaged foods. The packaged foods are loaded into carts and identified with the shipping document. This shipping document number is identified with a number and barcode. As packaged foods are shipped, the production associate scans the shipping document and the finished product barcode. | Records are stored as EPCIS Shipping Events. | Shipping records are stored in the external traceability network (link to network) as a digital record containing globally unique identifiers for finished products (GTIN-14s). The ship-from and ship-to location are identiifed using a globally unique identifier (GLNs). The traceability network shares the shipping KDEs to subsequent recipients. Customers can also access shipping KDEs by scanning the barcode on the new food produced.
2. Methods for Identifying FTL Foods
Purchased ingredients | Suppliers are asked to identify FTL foods either digitally through our external traceability network (link), on shipping documents, or on food packaging. Internally, we identify ingredients in bills of materials as FTL or non-FTL
Finished products | Finished goods are identified internally as FTL in product master records, externally in a traceability network (link) and on product packaging via QR Code.
3. TLC Assignment
Purchased ingredients | If suppliers have not provided a Traceability Lot Code, we use internal product identiifer plus PO plus PO Line Number plus Received Date to uniquely identify each received product.
Finished products | For finished goods, we create a Traceability Lot Code based on product identifier (GTIN-14) plus customer identifier (e.g., store code) plus production location (e.g., warehouse facility code) plus production date.
4. Point of Contact Information
Primary Corporate Contact | {Name or Role}, Contact Email, Contact Phone Number, Primary Contact Address
Secondary contacts by production location | {Location Code} {Name or Role}, Contact Email, Contact Phone Number, Physical Location Address {Location Code} {Name or Role}, Contact Email, Contact Phone Number, Physical Location Address {Location Code} {Name or Role}, Contact Email, Contact Phone Number, Physical Location Address {LocationCode} {Name or Role}, Contact Email, Contact Phone Number, Physical Location Address {Location Code} {Name or Role}, Contact Email, Contact Phone Number, Physical Location Address

## Pilot Plan
|  | Food Item 1 | Food Item 2 | Food Item 3 | Traceability Plan | Training | Incoming KDEs by Electronic Message | Product Labeling Rcv/Xform/Ship | KDE Capture Receiving | KDE Capture Transform | KDE Capture Shipping | Outgoing KDEs by Electronic Message | Sortable Spreadsheet Store/Generate
Participants
& Locations | 1. Supplier, Location | Item A | Item B | Item C | X | X | X | [5 empty] | X
| 2. Supplier, Location | Item D | Item E | Item F | X | X | X | [5 empty] | X
| 3. Supplier, Location | Item G | Item H | Item I | X | X | X | [5 empty] | X
| 4. DC Location | Food 1 | Food 2 | Food 3 | X | X | X | X | X | X | X | X | X
| 5. Retail Location | Store 1 | Store 2 | Store 3 | X | X |  |  | X |  |  | X | X
Pilot Goals | 1. Record keeping and procedures | {description}
| 2. Data sharing | {description}
| 3. Sortable Spreadsheets | {description}
| 4. Verification | {description}
| 5. Education | {description}
Start Date | 2024-06-01
End Date | 2024-06-30

## Technology Evaluation
|  | Traceability Plan | Training | Incoming KDEs by Electronic Message | Product Labeling Rcv/Xform/Ship | KDE Capture Receiving | KDE Capture Transform | KDE Capture Shipping | Outgoing KDEs by Electronic Message | Sortable Spreadsheet Store/Generate | Total Points
Tech Providers
{Force Rank} | 1. Tech Provider | 5 | 1 | 3 | 5 | 2 | 5 | 4 | 3 | 4 | 32
| 2. Tech Provider | 1 | 5 | 2 | 1 | 3 | 2 | 5 | 2 | 5 | 26
| 3. Tech Provider | 3 | 3 | 5 | 2 | 4 | 4 | 1 | 5 | 2 | 29
| 4. Tech Provider | 4 | 4 | 1 | 4 | 5 | 1 | 2 | 4 | 1 | 26
| 5. Tech Provider | 2 | 2 | 4 | 3 | 1 | 3 | 3 | 1 | 3 | 22

## Budget
| Traceability Plan |  | Training |  | Incoming KDEs by Electronic Message |  | Product Labeling Rcv/Xform/Ship |  | KDE Capture Receiving |  | KDE Capture Transformation |  | KDE Capture Shipping |  | Outgoing KDEs by Electronic Message |  | Sortable Spreadsheet Store/Generate |  | Subtotal
| One-time | Recurring | One-time | Recurring | One-time | Recurring | One-time | Recurring | One-time | Recurring | One-time | Recurring | One-time | Recurring | One-time | Recurring | One-time | Recurring | One-time | Recurring
Corporate | 5000 | 2500 | 5000 | 2500 | 5000 | 2500 | 2500 | 2500 | 5000 | 2500 | 5000 | 2500 | 5000 | 2500 | 5000 | 2500 | 5000 | 2500 | 42500 | 22500
Location B | 100 | 50 | 100 | 50 | 100 | 50 | 2500 | 2500 | 2500 | 1250 | 2500 | 1250 | 2500 | 1250 | 100 | 50 | 100 | 50 | 10500 | 6500
Location C | 100 | 50 | 100 | 50 | 100 | 50 | 2500 | 2500 | 2500 | 1250 | 2500 | 1250 | 2500 | 1250 | 100 | 50 | 100 | 50 | 10500 | 6500
Location D | 100 | 50 | 100 | 50 | 100 | 50 | 2500 | 2500 | 2500 | 1250 | 2500 | 1250 | 2500 | 1250 | 100 | 50 | 100 | 50 | 10500 | 6500
Location E | 100 | 50 | 100 | 50 | 100 | 50 | 2500 | 2500 | 2500 | 1250 | 2500 | 1250 | 2500 | 1250 | 100 | 50 | 100 | 50 | 10500 | 6500
Location F | 100 | 50 | 100 | 50 | 100 | 50 | 2500 | 2500 | 2500 | 1250 | 2500 | 1250 | 2500 | 1250 | 100 | 50 | 100 | 50 | 10500 | 6500
Location G | 100 | 50 | 100 | 50 | 100 | 50 | 2500 | 2500 | 2500 | 1250 | 2500 | 1250 | 2500 | 1250 | 100 | 50 | 100 | 50 | 10500 | 6500
Location H | 100 | 50 | 100 | 50 | 100 | 50 | 2500 | 2500 | 2500 | 1250 | 2500 | 1250 | 2500 | 1250 | 100 | 50 | 100 | 50 | 10500 | 6500
Location I | 100 | 50 | 100 | 50 | 100 | 50 | 2500 | 2500 | 2500 | 1250 | 2500 | 1250 | 2500 | 1250 | 100 | 50 | 100 | 50 | 10500 | 6500
Location J | 100 | 50 | 100 | 50 | 100 | 50 | 2500 | 2500 | 2500 | 1250 | 2500 | 1250 | 2500 | 1250 | 100 | 50 | 100 | 50 | 10500 | 6500
Location K | 100 | 50 | 100 | 50 | 100 | 50 | 2500 | 2500 | 2500 | 1250 | 2500 | 1250 | 2500 | 1250 | 100 | 50 | 100 | 50 | 10500 | 6500
Location L | 100 | 50 | 100 | 50 | 100 | 50 | 2500 | 2500 | 2500 | 1250 | 2500 | 1250 | 2500 | 1250 | 100 | 50 | 100 | 50 | 10500 | 6500
[19 empty] | 158000 | 94000
One-Time Costs: | Hardware, perpetual licensed software, consulting, leadership time, staff time, training material development, other one-time costs
Recurring Costs: | Hardware maintenance, subscription software, third party support, label media, staff time, other recurring costs

## Project Plan
| PS | PL | TM | TM | TM | TM
| Person 1 | Person 2 | Person 3 | Person 3 | Person 4 | Person 5
Roles
PS - Project Sponsor
PL - Project Lead
TM - Team Member | [9 empty] | Jun |  |  |  |  | 2024-07-06 |  |  |  | 2024-08-03 |  |  |  |  | 2024-09-07 |  |  |  | 2024-10-05
| Responsibilities (RACI) | [5 empty] | Start | End | Compl | 2024-06-01 | 2024-06-08 | 2024-06-15 | 2024-06-22 | 2024-06-29 | 2024-07-06 | 2024-07-13 | 2024-07-20 | 2024-07-27 | 2024-08-03 | 2024-08-10 | 2024-08-17 | 2024-08-24 | 2024-08-31 | 2024-09-07 | 2024-09-14 | 2024-09-21 | 2024-09-28 | 2024-10-05 | 2024-10-12 | 2024-10-19 | 2024-10-26
Supplier Engagement
Communicate Requirements | A | A | R | R | C | I | 2024-06-01 | 2024-07-12 | 50% | L | W | O | O | P | P
Sample Test Deliveries | A | A | R | R | C | I | 2024-06-22 | 2024-07-26 | 15% |  |  | O | O | P | P | P | P
Setup Receiving Process
Create Traceability Plan for Receiving | A | A | R | R | C | I | 2024-06-29 | 2024-08-09 | 0% |  |  |  |  | P | P | P | P | P | P
Establish Receiving Record Capture Systems | A | A | R | R | C | I | 2024-06-29 | 2024-08-09 | 0% |  |  |  |  | P | P | P | P | P | P
Develop Training Materials for Receivers | A | A | R | R | C | I | 2024-06-29 | 2024-08-09 | 0% |  |  |  |  | P | P | P | P | P | P
Test Receiving Systems | A | A | R | R | C | I | 2024-06-29 | 2024-08-09 | 0% |  |  |  |  | P | P | P | P | P | P
Start Receiving Process | A | A | R | R | C | I | 2024-06-29 | 2024-08-09 | 0% |  |  |  |  | P | P | P | P | P | P
Responsibilities (RACI) Legend: | [8 empty] | Project Status Legend:
R - Responsible for doing the work to complete the task | [8 empty] | L | Late
A - Accountable or ultimately answerable for the task | [8 empty] | W | Warning, risk of being late
C - Consulted in the decision or designing the solution (two way communication) | [8 empty] | O | On-time
I - Informed of the decision or solution (one way communication) | [8 empty] | P | Planned

## Shipping KDEs
Electronic Sortable Spreadsheet ¦ Shipping Records from Distributor to Grocery Store
(1) GTIN-14 | (1) Lot or Batch Number | (1) Date Code* | (1) Date Type* | (2) Qty | (2) UOM | (3) Product Description | (4) Ship-To Location | (4) Ship-To Location GLN | (5) Ship-From Location | (5) Ship-From Location GLN | (6) Ship Date | (7) TLC Source Reference - GLN | (7) TLC Source Name | (8) Ref Doc
30071430011062​ | ABC123 | 230726 | PACK DT | 10 | Meals | Mixed Green Salad Kit SKU #8901 | XYZ Grocery | 5000478096429 | ABC Distribution Company | 3007149012321 | 2023-07-26 | 3007149012321 | ABC Distribution Company | PO 1234

## Receiving KDEs
Electronic Sortable Spreadsheet ¦ Receiving Records from Supplier to Distributor
(1) GTIN-14 | (1) Lot or Batch Number | (1) Date | (1) Date Type | (1) SSCC* | (2) Qty | (2) UOM | (3) Product Description | (4) Ship-From Location | (4) Ship-From Location GLN | (5) Receive Location | (5) Receive Location GLN | (6) Receive Date | (7) TLC Source Reference - GLN | (7) TLC Source Name | (8) Ref Doc
30071430011059​ | 2071231339 | 230723 | HARVEST DT | 103338389000000677 | 100 | Cases | Romaine Lettuce Hearts | Bob's Supply Co | 9517435978203 | ABC Distribution Company | 3007149012321 | 2023-07-25 | 1234567890123​ | Tom's Packing Shed | PO 82349
30692006512298 | 3057813607 | 230720 | PACK DT | 103338389000000754 | 50 | Cases | Tomatoes | Bob's Supply Co | 9517435978203 | ABC Distribution Company | 3007149012321 | 2023-07-24 | 3537867890781​ | Terri's Tomato Packing | PO 82332
16872597436009 | 8059431227 | 231005 | EXPRY DT | 103338389000000834 | 40 | Cases | Feta Cheese | Bob's Supply Co | 9517435978203 | ABC Distribution Company | 3007149012321 | 2023-07-20 | 6784547823678​ | CheeseCo Plant 86 | PO 82302

## Transformation KDEs
Electronic Sortable Spreadsheet ¦ Transformation Records at Processing Facility
(1)(i) FTL Food Used GTIN-14 | (1)(i) FTL Food Used Batch or Lot Number | (1)(ii) FTL Food Used Product Description | (1)(iii) FTL Food Used Qty | (1)(iii) FTL Food Used UOM | (2)(i) FTL Food Produced GTIN-14 | (2)(i) FTL Food Produced - Retail Item Number | (2)(i) FTL Food Produced - Lot or Batch Number | (2)(ii) Transform Location | (2)(ii) Transformation GLN | (2)(iii) Transformation Complete Date | (2)(iv) FTL Food Produced Product Description | (2)(v) FTL Food Produced Qty | (2)(v) FTL Food Produced UOM | (2)(vi) Ref Doc
30071430011059 | 2071231339 | Romaine Lettuce Hearts​ | 10 | Cases | 30071430011062 | SKU #8901 | ABC123 | Sue's Processing Facility​ | 3007149012321 | 230726 | Mixed Salad SKU #8901​ | 200 | Meals | WO-23923
30692006512298 | 3057813607 | Tomatoes | 6 | Cases | 30071430011062 | SKU #8901 | ABC123 | Sue's Processing Facility​ | 3007149012321 | 230726 | Mixed Salad SKU #8901​ | 200 | Meals | WO-23923
16872597436009 | 8059431227 | Feta Cheese | 4 | Cases | 30071430011062 | SKU #8901 | ABC123 | Sue's Processing Facility​ | 3007149012321 | 230726 | Mixed Salad SKU #8901​ | 200 | Meals | WO-23923
Note: If an FTL food was used to make the finished food item, KDEs for those items do not need to be recorded here